## Gantt
MXEN3002 Lab Project — Gantt (P.1)
Five weekly 3h sessions to 70/70. Bars are colour-coded by session; dates are indicative — set them to your lab timetable.
Timeline → |  |  |  | Prep |  |  |  |  | Week 2 | [5 empty] | Week 3 |  |  |  |  | Week 4 |  |  |  | Week 5 |  |  |  |  | Week 6
Session | Milestone(s) | Week | Marks | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27
Prep (done) | Read docs + IO maps | Prep | 0
Prep (done) | FB design + FSM design | Prep | 0
Prep (done) | ST / PLCopen / docs | Prep | 0
Session 1 | P.1 Gantt + strategy | Week 2 | 1
Session 1 | 1.1 tick-tock sample | Week 2 | 1
Session 1 | 1.2 / 1.3 purpose + interface | Week 2 | 2
Session 1 | 1.4 panel FSM | Week 2 | 2
Session 1 | 1.5 / 1.6 arm proper + robust | Week 2 | 4
Session 1 | 1.7 / 1.8 ejector proper + robust | Week 2 | 4
Session 2 | 1.9 / 1.10 station proper + robust | Week 3 | 6
Session 2 | 1.11 revise Gantt | Week 3 | 1
Session 2 | S1.1 / S1.2 SCADA | Week 3 | 5
Session 2 | 2.1 purpose | Week 3 | 1
Session 2 | 2.2 / 2.3 lift (reuse T1) | Week 3 | 2
Session 3 | 2.4 / 2.5 ejector T3 | Week 4 | 4
Session 3 | 2.6 / 2.7 station proper + robust | Week 4 | 5
Session 3 | 2.8 revise Gantt | Week 4 | 1
Session 3 | S2.1 / S2.2 SCADA | Week 4 | 5
Session 4 | 3.1 / 3.2 station proper + robust | Week 5 | 3
Session 4 | 3.3 robust | Week 5 | 3
Session 4 | 3.4 revise Gantt | Week 5 | 1
Session 4 | S3.1 / S3.2 SCADA | Week 5 | 5
Session 4 | L.1 FB reuse demo | Week 5 | 3
Session 5 | L.2 line proper | Week 6 | 5
Session 5 | L.3 line robust | Week 6 | 6
Mark-claim summary
Session | Claim |  | Marks
Session 1 | P.1, 1.1–1.8 |  | 14
Session 2 | 1.9, 1.10, 1.11, S1.1, S1.2, 2.1, 2.2, 2.3 |  | 15
Session 3 | 2.4–2.8, S2.1, S2.2 |  | 15
Session 4 | 3.1–3.4, S3.1, S3.2, L.1 |  | 15
Session 5 | L.2, L.3 |  | 11
TOTAL |  |  | 70